## Test Case - Bus Reservation (Ad
Product Name |  |  | Bus Reservation (Admin Panel) | TC Start Date | 2026-02-05 | TC Execution Start Date | 2026-02-05 | TEST CASE SUMMARY
Module Name |  |  | Auth - Sign In, Log Out, Forgot Password, Notification, Email, Reservation, Search, Filter, Internal Offers, Send Payment Link | TC End Date | 2026-02-08 | TC Execution End Date | 2026-02-10 | P | 59
|  |  |  | Test Case Developed By | Tahsin Ahmed | App (Tested) | Mobile App | F | 0
Developer Name (TL) |  |  | Shovi | Test Case Reviewed By |  |  |  | N | 2
Test Executed by | [7 empty] | Total | 61
Test Case ID/Name | Module | Test Case Description with Scenario | Precondition | Test Data | Step Description | Expected Result | Actual Result | Status | Screenshot | Comment
TC-01 | Auth | Sign In |  | Input - Valid Email (tahsinahmed309203@gmail.com) | Input - Valid Data in Email Address Field. | Proper Error Message should be given for the User. Also User can not "Sign In" without Email and Password. | User has given valid Email Address ("tahsinahmed309203@gmail.com") and click on "Sign In - Button". Error Message has given ("Error! - Please enter email and password."). | P
TC-02 |  |  |  | Input - Valid Password (tahsin12345) | Input - Valid Data in Password Field. | Proper Error Message should be given for the User. Also User can not "Sign In" without Email and Password. | User has given valid Password ("tahsin12345") and click on "Sign In - Button". Error Message has given ("Error! - Please enter email and password."). | P
TC-03 |  |  |  | No Input - Email and Password | No Input - Email and Password | Proper Error Message should be given for the User. Also User can not "Sign In" without Email and Password. | User has not given any data of Email Address and Password and click on "Sign In - Button". Error Message has given ("Error! - Please enter email and password."). | P
TC-04 |  |  |  | Input - Invalid Email (tahsin.ahmed.3092@yahoo.com) and Valid Password (tahsin12345) | Input - Invalid Data in Email Address Field and Valid Password. | Proper Error Message should be given for the User. Also User can not "Sign In". | User has given invalid Email Address ("tahsin.ahmed.3092@yahoo.com") with valid Password ("tahsin12345') and click on "Sign In - Button". Error Message has given ("Login Failed - User not found"). | P
TC-05 |  |  |  | Input - Invalid Email (01732636945) and Valid Password (tahsin12345) | Input - Invalid Data in Email Address Field and Valid Password. | Proper Error Message should be given for the User. Also User can not "Sign In". | User has given invalid Email Address ("017332636945") with valid Password ("tahsin12345') and click on "Sign In - Button". Error Message has given ("Error! Please enter a valid email"). | P
TC-06 |  |  |  | Input - Valid Email (tahsinahmed309203@gmail.com) and Invalid Password (123456a) | Input - Valid Data in Email Address Field and Invalid Password. | Proper Error Message should be given for the User. Also User can not "Sign In". | User has given valid Email Address ("tahsinahmed309203@gmail.com") with valid Password ("123456a') and click on "Sign In - Button". Error Message has given ("Login Failed - Incorrect password"). | P
TC-07 |  |  |  | Input - Invalid Email (tahsinahmed309203@gmail.com@) and Invalid Password (123456a) | Input - Invalid Data in Email Address Field and Invalid Password. | Proper Error Message should be given for the User. Also User can not "Sign In". | User has given invalid Email Address ("tahsinahmed309203@gmail.com@") with invalid Password ("123456a') and click on "Sign In - Button". Error Message has given ("Error! Please enter a valid email"). | P
TC-08 |  |  |  | Show / Hide - Button | Show / Hide - Button. | Data should be given properly. | User can Show / Hide text as well as the specification. | P
TC-09 |  |  |  | Input - Valid Email (tahsinahmed309203@gmail.com) and Valid Password (tahsin12345) | Input - Valid Data in Email Address Field and Valid Password. | Should be Logged In | User has given valid Email Address ("tahsinahmed309203@gmail.com") with valid Password ("tahsin12345') and click on "Sign In - Button". Success Message has given ("Success! - Login successful. Redirecting..."). After logged in it redirects User to the Dashboard page. | P
TC-10 | Auth | Log Out |  | Log Out - Button | Log Out - Button. | User should be logged out from the account. | User click on "Log Out - Button" from upper right side of the "Profile - Icon" where ("Name, Email, and Log Out Button) is visibled. System is logged out the User from the account. | P
TC-11 | Auth | Forgot Password | Not Exist User | Input - Invalid Email (01732636945) | Input - Invalid Data in Email Address Field. | After click on "Submit - Button" porper error message should be given. | User has given invalid Email Address ("01732636945") and click on "Submit - Button". Error Message has given ("Error! - Please enter a valid email address."). | P
TC-12 |  |  |  | Input - Invalid Email (tahsinahmed309203@gmail.com@) | Input - Invalid Data in Email Address Field. | After click on "Submit - Button" porper error message should be given. | User has given invalid Email Address ("tahsinahmed309203@gmail.com@") and click on "Submit - Button". Error Message has given ("Error! - Please enter a valid email address."). | P
TC-13 |  |  |  | Input - Valid Email (tahsinahmed3092033@gmail.com) | Input - Valid Data in Email Address Field for not Exist User. | After click on "Submit - Button" porper error message should be given. | Error message has given ("Error - No account found with this email address. Please check your email and try again."). | P
TC-14 |  |  | Exist User | Input - Valid Email (tahsinahmed3092033@gmail.com) | Input - Valid Data in Email Address Field for Existing User. | It should be redirected User to the Reset Password page. | After click on "Submit - Button", it redirect User to the "Reset Password" page with success message ("Success! - Reset code has been sent. Please check the email sent to ("Email Address"). OTP has sent to the Email Address. | P
TC-15 |  |  | Reset Code | Reset Code - Valid (OTP) | Reset Code - Valid (OTP) without Other Field. | Password should not be changed. | User do not fill up the other details, only give "Reset Code - 390073" and click on "Reset Password - Button". Error message has given ("Error! - Please fill in all field."). | P
TC-16 |  |  |  |  | Reset Code - Valid (OTP) without Confirm New Password. | Password should not be changed. | User do not fill up the other details, only give "Reset Code - 390073", "New Password - 12345678", and click on "Reset Password - Button". Error message has given ("Error! - Please fill in all field."). | P
TC-17 |  |  |  |  | Reset Code - Valid (OTP) without New Password. | Password should not be changed. | User do not fill up the other details, only give "Reset Code - 390073", "Confirm New Password - 12345678", and click on "Reset Password - Button". Error message has given ("Error! - Please fill in all field."). | P
TC-18 |  |  |  | Reset Code - Invalid (OTP) | Reset Code - Invalid (OTP). | Password should not be changed. | Give "Reset Code - 182932", "New Password - 12345678", "Confirm New Password - 12345678", and click on "Reset Password - Button". Error message has given ("Error - Invalid reset code"). | P
TC-19 |  |  |  | Reset Code - Expire (OTP) | Reset Code - Expire (OTP). | Password should not be changed. | Give "Reset Code - 182932", "New Password - 12345678", "Confirm New Password - 12345678", and click on "Reset Password - Button". Error message has given for "Expiration". | P
TC-20 |  |  |  | Reset Code - Valid (OTP) | Reset Code - Valid (OTP). | Password should be changed. | Give "Reset Code - 182931", "New Password - 12345678", "Confirm New Password - 12345678", and click on "Reset Password - Button". Success message has given ("Success! - Password has been reset successfully. Please sign in with your new password."). User can signed in with new password given and it redirects User to the Dasboard page. | P
TC-21 |  |  |  | Reset Code - Valid (OTP) with Previous Password | Reset Code - Valid (OTP) with Previous Password. | Password should be changed. | Give "Reset Code - 182931", "New Password - 12345678", "Confirm New Password - 12345678", and click on "Reset Password - Button". Success message has given ("Success! - Password has been reset successfully. Please sign in with your new password."). User can signed in with new password given and it redirects User to the Dasboard page. But previous used Password can bot be regenerated as "New Password". | N |  | We are not storing Previous Password.
TC-22 |  |  |  | Reset Code - Valid (OTP): Mismatch Password | Reset Code - Valid (OTP): Mismatch Password. | Password should not be changed. | Give "Reset Code - 182931", "New Password - 12345678", "Confirm New Password - 1234567", and click on "Reset Password - Button". Error message has given ("Error! - Passwords do not match."). | P
TC-23 |  |  |  | Show / Hide - Button | Show / Hide - Button. | Data should be given properly. | User click on "Show / Hide - Button", data has shown properly. | P
TC-24 |  |  |  | Back - Button | Back - Button. | Should be redirected User to the previous page. | It redirects User to the credential page. | P
TC-25 |  |  |  | Expiration - Reset Code | Expiration - Reset Code. | Reset Code should be expired after 15 minutes. | Error message has given which is correct. | P
TC-26 |  |  |  | Reset Email | Reset Email. | User should be get the Email for Reset Code. | User has get the Reset Code. | P
TC-27 | Notification | Notification |  |  | Notification will Generate. | Notification will generate as "Red Dot - Mark". | Notification is generated when User is requesting for reservation the Bus. | P
TC-28 |  |  | Mark All As Read | Mark All As Read - Button | Mark All As Read - Button. | Notification will count as "Read" already. | After click on "Mark All As Read - Button", "Dot - Icon" is gone. | P
TC-29 |  |  |  | Mark All As Read - Button (Serial) | Mark All As Read - Button (Serial). | Serial should be Up-To-Date. | Srial is updated properly. | P
TC-30 |  |  |  | Other Admin | Other Admin. | Other Admin should not get the notification of other Admin. | Right now all Admin get the notification. This cases which is not implemented yet. | N |  | Notification should get specific User.
TC-31 | Email | Email |  | Email - User (Reservation) | Email - User (Reservation). | User reservation for the Bus and Email should get by the Admin. | Email has got by the Admin. | P
TC-32 |  |  |  | Email - Agent Assign | Email - Agent Assign. | Admin should get the Email. | Email has got by the Admin. | P
TC-33 | Reservation | Reservation | Update Status | Reservation - View | Reservation - View. | Click on "View - Button", it should be redirected User to the "Details - Page". | It redirects User to the "Details - Page". | P
TC-34 |  |  |  | Cancel Reservation | Cancel Reservation. | Click on "Cancel Reservation - Button", it should be cancelled. | User click on "Cancel Reservation - Button", warning modal has given. If User click on "No, Keep Reservation - Button or Cross Icon" - Modal has gone and reservation is not cancelled. If User click on "Yes, Cancel Reservation - Button" - Modal has gone and given success message ("Success - Reservation cancelled successfully"). Also status is updated from "New" to "Cancelled". User back to the Reservation page data is removed in real-time. | P
TC-35 |  |  |  | Update Status - Assign Agent | Update Status - Assign Agent. | Agent should be assigned properly. | Tap on "Assign Agent", need to select Agent which is listed. Click On "Assign Agent - Button". Success message has given ("Success - Agent assigned successfully and status updated to in-progress"). | P
TC-36 |  |  |  | Update Status - Assign Agent (Cancel) | Update Status - Assign Agent (Cancel). | Data should be removed. | When User click on "Cancel - Button", data is removed also when User click on "Cross Icon", data is removed. | P
TC-37 |  |  |  | Update Status - Cancel | Update Status - Cancel. | Status should be changed. | User change the status from New to Cancel and status is changed with success message ("Success - Status updated successfully"). | P
TC-38 |  |  |  | Update Status - Cancel to New | Update Status - Cancel to New. | Status should be changed. | User change the status from Cancel to New and status is changed with success message ("Success - Status updated successfully"). | P
TC-39 |  |  |  | Update Status - New | Update Status - New. | Button should be disabled. | Button is "Disabled". | P
TC-40 |  |  |  | Update Status - In Progress | Update Status - In Progress. | Status should be changed. | When User assigned the Agent that time status is changed from New to In Progress. | P
TC-41 |  |  |  | Update Status - In Progress to Cancel | Update Status - In Progress to Cancel. | Status should be changed. | When User change the status that time status is changed from In Progress to Cancelled. | P
TC-42 |  |  |  | Update Status - In Progress to Cancel to New | Update Status - In Progress to Cancel to New. | Status - New should not given. | Status is changed properly. | P
TC-43 | Search | Search |  | Search by ID, Route, and Name | Search by ID, Route, and Name. | Should be searched properly and when no data found then proper message should be given. | Search by Route and Name is working. Also if there is no data found then proper message has given like ("No Data Found!"). | P
TC-44 | Filter | Filter |  | Filter | Filter | Filter should be working properly. Also if there is no data then proper message should be given. | Filter is working properly. If there is no data then proper message has given. | P
TC-45 | Internal Offers | Add Offers |  | Input - No Data | Input - No Data. | Offer should not be added. | Error message has given which is correct ("Error - Please fill in all fields"). | P
TC-46 |  |  |  | Input - Bus Company Name (Shymoli / Desh Travels / S. Alam) | Input - Bus Company Name (Shymoli / Desh Travels / S. Alam) without Other Required Field. | Offer should not be added. | Error message has given which is correct ("Error - Please fill in all fields"). | P
TC-47 |  |  |  | Input - Vehicle Details (No-AC Economy) | Input - Vehicle Details | Offer should not be added. | Error message has given which is correct ("Error - Please fill in all fields"). | P
TC-48 |  |  |  | Input - Price | Input - Price | Negative, Character, Decimal - Number should not be given. | Right now it's not taken. | P
TC-49 |  |  |  | Input - Offer Validity | Input - Offer Validity | Past Date (Journey Date) should not be taken. Only take Present and Future. | Past date it's not taken. | P
TC-50 |  |  |  | Input - Offer Validity (30/2/2026) | Input - Offer Validity | Should not be taken wrong date. | Offer Validity is working properly. After or Before "Journey Date" offer will not be validable. | P
TC-51 |  |  |  | Input - Notes | Input - Notes | Offer should not be added. | Error message has given which is correct ("Error - Please fill in all fields"). | P
TC-52 |  |  |  | Input - All Required Fields | Input - All Required Fields. | Offer should be added. | Offer added successfully with proper message ("Success - Offer added successfully"). | P
TC-53 |  |  |  | Delete - Offer | Delete - Offer. | Offer should be deleted. | Offer is deleted when User click on "Delete - Button". | P
TC-54 |  |  |  | Offer - Sent | Offer - Sent. | Proper status should be given. | When Agent "Send Offer" to the User that time "Offer Status - Sent" has shown. | P
TC-55 |  |  |  | Offer - Rejected | Offer - Rejected. | Proper status should be given. | When User "Rejected Offer" to the Agent that time "Offer Status - Rejected" has shown. | P
TC-56 |  |  |  | Offer - Accepted | Offer - Accepted. | Proper status should be given. | When User "Confirmed Offer" to the Agent that time "Offer Status - Accepted" has shown. | P
TC-57 | Send Payment Link | Send Payment Link |  | Send Payment Link | Send Payment Link. | Modal should be open with proper details. | Modal has opened when User click on "Send Payment Link". | P
TC-58 |  |  |  | Send Payment Link - Payment Amount | Send Payment Link - Payment Amount. | Negative, Character, Negative or Positive (+ / -) sign should not be acceptable. | Right now User can't write (- / +) icon with number. Also User write ("1") and Close / Cross Icon (Click On) the modal and again reopen the modal cache data has taken. User write down in the input field ("1") and remove it or click on backspace (Keyboard), auto 2000 amount has given. | P |  | Connect with Agent Panel.
TC-59 |  |  |  | Send Payment Link - Payment Amount | Send Payment Link - Payment Amount. | Payment Link should be get by the User Email. | User has got the Payment Link in His / Her - Email. | P
TC-60 |  |  |  | Send Payment Link - Email | Send Payment Link - Email. | Payment should be successful at one time. | User done it properly with bKash. | P
TC-61 |  |  |  | Send Payment Link - Email | Send Payment Link - Email. | Payment should be successful at one time. | User tried to click on used link for payment that time error message has given ("This payment has already been completed."). | P